## Ark1
Lofthus frukt & Saft |  |  | 2019-11-10 |  |  |  |  | 2019-11-18 |  |  |  |  | 2019-11-25 |  |  |  |  | 2019-12-02 |  |  |  |  | 2019-12-09
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday
Task: | People assigned: | Duration:
Planning
Client meeting and brifing | whole team (with Project manager) | 1 d
Research | Digital marketing manager | 5d | Research and plan - target audience, marketing, budget, soc.med
| FE developer | 3d | brainstorming, research
| BE developer | 5d | hosting the domain, making the database
| Photographer | 3d | Planning the photo/video presentation
Team meeting with task timeline | whole team (with Project manager) | < 1d
Photo and video
Gathering photo and video material | Photographer | 4d |  |  |  | Recording the video about the company and production
|  | 2d |  |  |  | Apple orchard photos
Editing photo and video material | Photographer | 5d | [10 empty] | < Digital marketing manager has to be consulted about the content of the videos
Design
Moodboard, color palette, typography | FE developer | 3d
Website mockup | FE developer | 5d
| Digital marketing manager | 5d | [5 empty] | << to be consulted
| Photographer | 5d
Client meeting | Project manager, DM manager, FE dev | [11 empty] | << Getting client's imput on the content and design
Editing and finilizing the design mockup | FE developer | 2d
Content management
Identify the latest trends affecting the industry | Digital marketing manager | 5d
Reports about product's nutritional content | Digital marketing manager | 5d
Calculations for different shipping costs | Digital marketing manager | 5d
Marketing campain and social media | Digital marketing manager | 5d
Coding the page
HTML/CSS | FE Developer | 12d | [12 empty] | html/css
Log in for private/business customers | FE Developer | 3d
Different forms and shipping options (private/bus.) | FE Developer | 3d
SQL-statement to connect forms to database | BE Developer | 2d | [18 empty] | connect to database
Add photo and video | FE Developer | 3d
Set up Google Analytics |  | 2d
Software update | FE Developer | 2d
Privacy settings | FE Developer | 2d
Testing | FE, BE Developer | 1d | [22 empty] | testing
Launching | [26 empty] | launch day
Client meeting | whole team | < 1d
Launch day! | FE developer | 1d